## Slide 1: State of Montana Statewide 9-1-1 Plan Project
9-1-1 Advisory Council Meeting
September 12th, 2019

## Slide 2: Introductions
Federal Engineering
  Eric Parry, ENP - Program Manager

## Slide 3: Agenda Topics
Project Update
  Milestone Review
Strategy & Planning
  Advisory Council Adoption of Project Documents
  Advisory Council Recommendation Request
PSAP Outreach
  PSAP Engagement
  Tribal PSAP Assessments

## Slide 4: Project Update
Milestone Deliverables | 
Milestone 1: | Completion of Project Plan and Communications Plan
Milestone 2A: | Completion of First Half of Stakeholder Engagement (PSAP surveys, town hall meetings & PSAP visits/interviews)
Milestone 2B: | Completion of Second Half of Stakeholder Engagement (PSAP surveys, town hall meetings & PSAP visits/interviews)
Milestone 3: | PSAP Inventories
Milestone 4: | ESInet Inventory
Milestone 5: | NG9-1-1 Technology Standards and Requirements
Milestone 6: | PSAP Needs Assessments
Milestone 7: | ESInet Design and Implementation Plan

## Slide 5: Progress to Date
ESInet Inventory (Milestone 4)
  Captured and documented status of the existing statewide 9-1-1 network, current network diagrams, maps and current bandwidth availability and utilization
  Documented existing ESInet inventory
Action Item:
  Advisory Council Recommendation for Adoption

## Slide 6: Progress to Date
NG9-1-1 Technology Standards and Requirements (Milestone 5)
  Recommended standards to the State for ESInet, network security, GIS data, call delivery, and call processing based on NG9-1-1 national standards
  Developed a preliminary set of NG9-1-1 technology requirements
Action Item:
  Advisory Council Recommendation for Adoption

## Slide 7: Progress to Date
PSAP Inventories & Needs Assessment (Milestone 6)
  Documented existing inventory and readiness of PSAPs for evolution to NG9-1-1
  Developed summary of survey data and interview results from each PSAP
  Identified technology, hardware, and software upgrades necessary for PSAP to become NG9-1-1 capable
  Developed transition pathway to NG9-1-1 for each PSAP
Action Item:
  Advisory Council Recommendation for Adoption

## Slide 8: Progress to Date
NG9-1-1/ESInet Design and Implementation Plan (Milestone 7)
  Validated ESInet requirements
  Developed recommended requirements, designs and implementation options for a statewide ESInet
Action Item:
  Advisory Council Recommendation for Adoption

## Slide 9: PSAP Outreach
PSAP Engagement
  Continued engagement of PSAP stakeholder community
  Town Hall Meetings
Tribal PSAP Assessments
  PSAP visit and assessment of readiness for evolution to NG9-1-1

## Slide 10: Next Steps Options
ESInet Procurement and Deployment Strategy: Other State Experiences
10

## Slide 11: State of Montana Statewide 9-1-1 Plan Project
Federal Engineering
Stands Ready to Assist &
Thanks You for this Opportunity